## Project Plan
Final Project
Project Lead: Shared
Features and Description | Estimated Implementation | Assigned To | Status
Not Implemented
In Progress
Done
USER INTERFACE
In Game UI | 2021-11-24 | Zacari | In Progress
Menu Screens & Navigation | 2021-11-17 | Zacari | Done
Pause Menu | 2021-11-17 | Zacari | Done
AUDIO
Menu Screen Music | 2021-11-24 | Zacari | Not Implemented
In Game Music | 2021-11-24 | Zacari | Done
SFX
Button Hover & Click | 2021-11-17 | Zacari | Done
Key Presses | 2021-11-24 | Zacari | Done
Player Hurt | 2021-11-24 | Zacari | Done
Player Jump | 2021-11-24 | Zacari | Done
Enemy Destroyed | 2021-11-24 | Zacari | Done
PROGRAMMING
Character Movement | 2021-11-10 | Michael | Done
Enemy Movement | TBD | Jennifer | Not Implemented
Camera Movement | 2021-11-17 | Michael | Done
Damage & Health | TBD | Zacari | In Progress
Collisions - Player & Enemy | TBD | Zacari | In Progress
ART
Animations | 2021-11-24 | Jennifer | Not Implemented
Tileset | Ongoing | Jennifer | In Progress
Character | 2021-11-17 | Jennifer | In Progress
Enemies | 2021-11-17 | Jennifer | In Progress
DESIGN
Map Layout | TBD | Michael & Jennifer | In Progress
Secret Room Placement | TBD | MJZ (Zacari & Michael) | In Progress
Enemy Placement | TBD | MJZ (Zacari) | In Progress
Key Placement | TBD | MJZ (Zacari & Michael) | In Progress